## Automata-1-Moore
WP name | Task name | Notes | Dependencies | Resources | Assignees | Day 1 | Day 2 | Day 3 | ...
WP1 - Board design | T1.1 - Turn on embedded LEDs |  | - | Board
| T1.2 - Blink embedded LEDs |  | T1.1 | Board
| T1.3 - Create circuit for GPIO LEDs |  | - | Board, Breadboard, LEDs, Resistances
| T1.4 - Turn on GPIO LEDs |  | T1.3 | Board, Breadboard, LEDs, Resistances
| T1.5 - Blink GPIO LEDs |  | T1.3, T1.4 | Board, Breadboard, LEDs, Resistances
| T1.6 - Enable debugging via UART |  | - | Board
WP2 - SW development | T2.1 - Develop AUTOMATA1 on Laptop |  | - | -
| T2.2 - Develop simple automata on Board IDE (ex: STM Cube) | Here, we need just to test that we can work on the IDE | - | Board
WP3 - Integration | T3.1 - Port AUTOMATA1 on target board |  | T2.1, T2.2 | Board, AUTOMATA1 source code (from outsorcing?)
| T3.2 - Port AUTOMATA1 on target board, and include GPIO |  | T3.1, T1.5 | Board, Breadboard, LEDs, Resistances
WP4 - Documentation | T4.1 - Write documentation for HW
T4.2 - Write documentation for SW
| T4.3 - Write documentation for Arduino |  |  |  | Prof. Burgio